## PRODUCT BACKLOG
ID | USER STORY | ACCEPTANCE CRITERIA | STATUS | DATE
H1 | Create GIT repository | - repository with name hydra should be created on GITHUB - repository should be empty with only a readme file | DONE | 2016-02-16
H2 | Create SAILS project structure | - create docs, src and test folders - create basic sails project - setup database | DONE | 2016-02-16
H3 | Create Models as per design
H4 | As a user, I would like to create a component so that other users can use it | - component name must be unique - mandatory fields are name, description, owner, category - created date is mandatory and must be auto inserted
H5 | As a user, I would like to add one or more versions to a component
H6 | As a user, I would like to download a specific version of a component
H7 | As a user, I would like to rate a specific version of a component
H8-1 | As a user, I would like to search for components based on category, name
H8-2 | As a user, I would like to search for components based on top rated
H8-3 | As a user, I would like to search for components based on most downloaded
H9 | As a user, I would like to de-activate a version of a component
H10 | As a hydra admin, I would like to create new categories and list them so that a user can categorize a component into one of them | - insert new category into database - category must be unique. No duplicates allowed - list all categories available | DONE | 2016-02-18
H11 | List all components | - list all components that are active